Attachment 6

Architectural Part Survey Report Ver.1 The Program for the Establishment of a Project Name (Period/Budget)

Month 20xx

Name

Affiliation

Contents

Contents

Ⅰ. Summary of report	○

1. Overview of architectural part survey

Ⅱ. Review of proposed project site	○

1. Information on project site

2. Analysis of project site and surrounding area

3. Analysis of infrastructure status

Ⅲ. Survey of similar local building facilities 	○

1. Similar building facility - 1

2. Similar building facility - 2

Ⅳ. Architectural plan and guidance	○

1. Architectural plan

2. Commitments by both participants for construction (draft)

Ⅴ. Survey on local construction conditions ○

1. General conditions for building Projects

2. Status of design performance level and design firms

3. Status of construction activities and construction companies

4. Status of supervision system

Ⅵ. Calculation of architectural part costs	○

1. Summary of architectural part costs

2. Determining construction unit cost

3. Estimated architectural part costs

Ⅶ. Time schedule of project implementation	○

1. Time schedule of project implementation (draft)

2. Design period

3. Construction period

4. Handover and defects liability period

Ⅷ. Risk factors and countermeasures	○

1. Planning phase

2. Design bidding and design phase

3. Construction bidding and construction phase

4. Completion and O&M (operation & maintenance) phase

Appendices

Architecture - 1. Checklist

Architecture - 2. Data

[Glossary] (essential terms) ✱ In alphabetical order

| Abbreviation | Full description | Remarks |
| --- | --- | --- |
| ATS | Automated Transfer Switch |  |

Ⅰ. Summary of report

1. Overview of architectural part survey

1.1.  Summary of architectural part survey details

| Classification | Details |
| --- | --- |
| Project name | ▣ Establishment of Construction Sector Focused TVET (Technical and Vocational Education and Training) School in Province No. 2, Nepal |
| Proposed area / project site | ▣ Bardibas Municipality, Province No. 2, Nepal - Area to be developed as a technical education hub |
| Recipient | ▣ CTVET (Council for Technical Education and Vocational Training) under the Ministry of Education, Science and Technology (MOEST) in Nepal |
| Project Overview | ▣ Project site area: No information ▣ Type: New construction ▣ Total floor area: 5,000 m2 (3 engineering departments, lecture building, administrative building (including TITI/NVQS), training building, storage space, security building, exterior landscaping, etc.) ▣ Programs: 3 engineering departments for 3-year diploma course; 3 engineering departments for 18-month TSLC course; short-term course |
| Period / budget | ▣ Architectural project period: 2021–2026 (3 years) ▣ Architectural budget (provisional): USD 5,000,000 |
| Type | ▣ Project |
| Sector | ▣ Education |
| Purpose | ▣ Capacity-building of workers in the construction technology sector to meet required skills at home and abroad by constructing a construction sector focused TVET school in Province No. 2, contributing to increasing the employment rate and household income. |

1.2. Survey schedule and location

ㅇ Local survey

- Period/location:  Sun, Dec. 15 – Sat, Dec. 21, 2019 / Bardibas Municipality, Province No. 2, Nepal

1.3. Essential matters for further survey in the future

✱ Note: Specify if there is anything that was not confirmed in this survey and any essential matters for further survey in the future.

Ⅱ. Review of proposed project site

1. Information on project site

1.1. Location and address

✱ Note: Wide-area analysis by using site address, aerial photographs, and map

1.2. Relevant laws related with proposed project site

✱ Note: Check and summarize relevant laws and regulations, such as those related to urban planning, buildings, environment, fire services, altitude limit, cultural heritage management, medical facilities (if necessary). Include original text or excerpts of relevant laws as attachments to the report.

1.3. Cadastral map and boundary & topographical survey drawing

✱ Note: Check and confirm information on site area, shape, topography, obstacles, and boundaries.

1.4. Land ownership and ownership of existing buildings

✱ Note: Check whether there are ownership issues or not. If there is an existing building on the site, check the ownership and its retention status.

2. Analysis of project site and surrounding area

2.1. Status of surrounding area and relationship with surrounding facilities

✱ Note: Analyze influencing factors, such as conservation areas, linked facilities and public infrastructure as well as obstacles to project implementation.

2.2. Accessibility to project site

✱ Note: Accessibility to downtown and status of public transportation as well as width and pavement condition of the access road

3. Analysis of infrastructure status

3.1. Establishment of infrastructure

✱ Note: Survey must be conducted based on data, facts and interviews with pertinent parties. The installation plan must be confirmed by the department in charge.

| Classification |  | Requirement | Details |
| --- | --- | --- | --- |
| General building | Water supply | ✔ | - Check whether water can be supplied stably - Consider alternative methods (e.g. deep-well development, substitute water) if not available |
|  | Rainwater treatment | ✔ | - An area installed with rainwater pipes is recommended for facilities in downtown - Review the environment and influence of surrounding areas for natural drainage treatment |
|  | Sewage treatment | ✔ | - Plan rainwater piping and sewage piping separately as much as possible - Include plan for septic tank installation if there is no sewage treatment pipe |
|  | Power supply | ✔ | - Check for stable power supply - Consider alternative methods (e.g. photovoltaics, power generator) if not available |
|  | Heat source |  | - Check the types of main heat sources (e.g. gas, oil) and review the plan for necessary facilities |
| Hospital (further review) | Medical gas |  | - Check whether it is a central supply or a mobile type |
|  | Water quality | ✔ | - Check whether there is any lime or other contaminants (causes of medical equipment failure) |
|  | Incinerator |  | - Check the method of medical waste incineration - Include plan for a separate incineration facility if not available |
|  | Wastewater treatment |  | - Separate plan needed for medical wastewater piping and collecting well |

3.2. Climate and safety against disaster

✱ Note: Check the status of regular flooding, safety of boundary retaining wall, level difference, and fire lanes

3.3. Possibility of facility expansion in the future

✱ Note: Check the necessity of horizontal extension and the availability of spare site

3.4. Review of repairs and extension/renovation

✱ Note: Obtain information of the structural status on the existing building and check safety matters

Ⅲ. Survey of similar local building facilities

1. Similar building facility - 1

1.1. Project overview

| Facility name |  |
| --- | --- |
| Project site (coordinates; area) |  |
| Usage |  |
| Building information (structure; completion date) | ▣ Ferroconcrete structure; 1990 ▣ Architectural design: "bbb"; constructor: "bbb" |
| Details | ▣ 2nd floor (workshop), lecture building (3F), administrative building (2F), storage and livestock house (1F) |
| Scale (gross floor area; No. of floors) | No data |
| Construction costs | USD 4.6 million (estimated) |

1.2. Features, and pros/cons

✱ Note: Describe features and details with attachments (e.g. drawings, photos) of the facilities

1.3. Suggestion

✱ Note: Describe content that can be considered or applied to the new building obtained from the review of similar facilities and their data

2. Similar building facility - 2

2.1. Project overview

2.2. Features, and pros/cons

2.3. Suggestion

Ⅳ. Architectural plan and assignment of each party

1. Architectural plan (tentative)

✱ Note: It can be provided as reference data for selection of architect and to instruct project tasks in the future

1.1. Architectural overview

| Site area | m2 |
| --- | --- |
| Construction Type | New construction |
| Structure | Ferroconcrete (Rahmen) |
| Details | Three-story main building (administrative and class buildings), two-story study hall (3 workshops, etc.), security building, exterior landscaping, etc. |
| Scale (gross floor area; No. of floors) | Gross floor area: m2 Number of Floors: Number of Buildings: |

1.2. Major function

✱ Note: Collaboration with other experts needed; describe the detailed usage of each building and rooms

1.3. Space program ✱Note: Requires consultation with experts in other fields; check the area and number of necessary spaces and add spaces that are essential in each building (public areas, such as bathrooms, stairs, corridors) before finalizing the table

| Classification |  |  | Per person | Capacity | Rooms | Room area (m2/room) | Total area (m2) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Administrative | Principal's Room |  | 40 m2 | 1 | 1 | 40 | 40 |  |
|  | Reception | Reception | 20 m2 | 1 | 1 | 20 | 20 |  |
|  | Vice Principal's Room |  | 20 m2 | 1 | 1 | 20 | 20 |  |
|  | Accountant's Room |  | 8.0 m2 | 2 | 1 | 20 | 20 |  |
|  | TITI/NVQS Office |  | 8.0 m2 | 4 | 1 | 40 | 40 |  |
|  | Examination Officer’s Room |  | 8.0 m2 | 2 | 1 | 20 | 20 |  |
|  | Procurement Room |  | 8.0 m2 | 2 | 1 | 20 | 20 |  |
|  | Admin. Office |  | 8.0 m2 | 4 | 1 | 40 | 40 |  |
|  | Dispensary |  | 8.0 m2 | 2 | 1 | 20 | 20 |  |
|  | Meeting Room |  | 3.0 m2 | 15 | 1 | 40 | 30 |  |
|  | Storage |  | - |  | 3 | 20 | 60 |  |
|  | Control Room |  | 8.0 m2 | 2 | 1 | 20 | 20 |  |
|  | Subtotal |  |  |  |  |  | 380 |  |
| Faculty | Head of Department |  | 8.0 m2 | 1 | 4 | 20 | 80 |  |
|  | Instructor’s Room |  | 8.0 m2 | 4 | 4 | 40 | 160 |  |
|  | Assistant Instructor’s Room |  | 4.0 m2 | 4 | 4 | 20 | 80 |  |
|  | Coordinator Room |  | 8.0 m2 | 4 | 1 | 40 | 40 |  |
|  | Subtotal |  |  |  |  |  | 360 |  |
| Classrooms | Classroom |  | 1.5 m2 | 48 | 12 | 80 | 960 |  |
|  | Drafts Room |  | 3.0 m2 | 48 | 2 | 160 | 320 |  |
|  | Computer Room |  | 3.0 m2 | 24 | 3 | 80 | 240 |  |
|  | Library |  |  |  | 1 | 200 | 200 |  |
|  | Subtotal |  |  |  |  |  | 1,720 |  |
| Total area of assigned space (a) |  |  |  |  |  |  | 2,460 |  |
| Total area of public space (b = a × 30%) |  |  |  |  |  |  | 756 |  |
| Total area of main building (A = a + b) |  |  |  |  |  |  | 3,216 |  |
| Study Hall | Workshop |  | 15 m2 | 24 | 3 | 270 | 810 | 2 floors |
|  | Lecture Room |  | 5.0 m2 | 24 | 1 | 80 | 80 |  |
|  | Instructor's Room |  | 8.0 m2 | 6 | 2 | 50 | 100 |  |
|  | Lockers |  |  |  | 2 | 25 | 50 |  |
|  | Storage (including hazard storage) |  |  |  | 2 | 50 | 100 |  |
| Total area of assigned space (c) |  |  |  |  |  |  | 1,140 |  |
| Total area of public space (d = c × 10%) |  |  |  |  |  |  | 114 |  |
| Total area of study hall (B = c + d) |  |  |  |  |  |  | 1,254 |  |
| Annex | M&E Area (e) |  |  |  | 1 | 120 | 120 |  |
|  | Guard House (f) |  |  |  | 1 | 10 | 10 |  |
|  | Total area of annex (C = e + f) |  |  |  |  |  | 130 |  |
| Total area of premises (A + B + C) |  |  |  |  |  |  | 4,600 |  |

1.4. Considerations and suggestions for building layout

✱ Note: Briefly present a site layout plan. And provide required considerations in connection with relevant by-law and regulations.

1.5. Considerations and suggestions for floor plan

✱ Note: Present a block diagram of each floor of the building and provide any required considerations for floor planning of the building.

1.6. Considerations and suggestions for elevation plan

* Note: Describe survey details and make suggestions regarding differences in land elevation, relationship with surrounding buildings, etc.

1.7. Considerations and suggestions for local architectural culture and style

* Note: Describe matters that should be considered, depending on the climate as well as features and conditions of local architecture

2. 
Commitments by both participants for construction (draft)

✱ Note: This chapter will be included in the RoD as an attachment; modifiable according to each project's conditions and recipient's implementation timeframe can be described in detail.

2.1. Detailed description of work scope to be carried out by KOCIA

2.2. Detailed description of work scope to be carried out by recipient

| Classification | Details | Standard work |  |  |
| --- | --- | --- | --- | --- |
|  |  | KOICA | Recipient/timeframe |  |
| Site survey and data collection | Geotechnical investigation report Conducting geological survey | ○ |  |  |
|  | Boundary and topographical survey Conducting reconnaissance survey | ○ |  |  |
|  | Providing cadastral survey map of site |  | ○ | When selecting a site |
|  | Providing existing facility site plan Providing the arrangement plan of existing facilities |  | ○ |  |
| Removal of existing buildings | Demolition |  | ○ | During the design phase (before construction begins) |
|  | Demolition costs |  | ○ |  |
|  | Handling after demolition |  | ○ |  |
| Paving for roads and Site clearance | Installment and pavement of access roads |  | ○ | Design phase (before construction begins) |
|  | Site clearance |  | ○ |  |
| Infrastructure facilities | Water supply intake |  | ○ | Start of construction/ construction phase |
|  | Sewage and rainwater facility intake |  | ○ |  |
|  | Power intake |  | ○ |  |
|  | Telecommunications and Internet connection |  | ○ |  |
|  | Heat source supply |  | ○ |  |
|  | Waste disposal |  | ○ |  |
| Architecture | Design and construction | ○ |  |  |
|  | Supervision / CM | ○ |  |  |
|  | Fences (walls) | ○ |  |  |
|  | Main entrance | ○ |  |  |
|  | Landscaping, auxiliary civil engineering (elevated water tank, septic tank, etc.) | ○ |  |  |
|  | Emergency generator | ○ |  |  |
|  | Inner roads and pedestrian roads | ○ |  |  |
|  | Internal and external signs | ○ |  |  |
| Building permits | Permission and approval | (○) | ○ | During design phase, upon completion |
|  | Cooperation for permission and approval |  | ○ |  |
|  | Expenses for permission and approval | (○) | ○ |  |
| Tax exemptions | Duty |  | ○ | Upon occurrence |
|  | VAT |  | ○ |  |
| Cooperation for material transportation |  |  | ○ | Upon occurrence |

Ⅴ. Survey on local construction conditions

✱ Note: Utilize various local data & reference, from which local construction conditions can be understood. Specify the source of various data and reference utilized.

1. General conditions for building construction

✱ Note: Bidding methods for public procurement (architectural design company and constructor selection method), unit price of actual construction work of public or general buildings (classified according to building type and quality), and architecture-related laws and regulations

2. Status of design level and design firm

✱ Note: Visit the local architectural design company, and check and specify the following contents: present the appropriate unit price of construction work, design firm selection method, design cost calculation, relevant local laws, appropriate design period, experience in carrying out similar projects, method of construction cost estimation (quantity and unit price), contact information (email), company information (brochure), interview results, and obtained data

2.1. Results of interview with architect

2.2. Status and level of local design

3. Status of construction and construction company

✱ Note: Visit a quality local construction company, and check and specify the following contents: presents the survey results of executed construction costs, supply and demand status of major materials (imported materials status), company’s project history (public and international organization projects using PR materials such as the brochure), year-round construction suspension period (rainy season, holidays, etc.), contact information (email), company information (brochure), interview results, and obtained data

3.3. Results of interview with construction company

3.4. Status and level of local construction

4. Status of supervision system

✱ Note: Construction supervision costs, legal supervision requirement status, and qualification of supervisors (certificate, experience, etc.)

Ⅵ. Calculation of architectural part costs

1. Summary of architectural part costs

| Classification |  | Calculation |  | Basis |
| --- | --- | --- | --- | --- |
| Construction costs (A) = ① + ② |  | ① Total floor area (construction) × unit price (USD/m2) ② Incidental expenses : Landscaping, roads on premises, auxiliary site civil work (② = ① × 10–15%) |  | ▪ Should be based on the survey results of the actual construction cost of local buildings ▪ Should determine the unit price considering the final quality of the building to be built (first refer to cases of other aid organizations and public procurements, etc.) ▪ Should consider the extent of the increase in the construction work unit price due to fluctuations in inflation when construction work starts after 3 to 5 years, considering the start date of construction work ▪ Review VAT exemption and refund methods in advance |
| Service fees | Design (B) | Local company | (A) × about 3–7% | ▪ Should calculate design costs as a total amount compared to the construction costs ▪ Local geotechnical investigation and topographic survey expenses should be included |
|  | CM (C) | (A) × 7–10% |  | ▪ Should be classified into domestic-inside Korea (non-resident) and overseas-outside Korea (resident CM and non-resident group’s business travel) ▪ Should consist of personnel expenses, overhead expenses, technical fees, and direct expenses |
|  | Supervision (D) | (A) × 4–5% |  | ▪ Usually estimated and contracted as a total amount |
| Contingency fund (E) |  | (A) × 5–10% |  | ▪ Reserved fund for construction work |
| Total |  | USD |  |  |

2. Determining construction unit cost

2.1. Consideration level of standard building unit price

* Note: Set the standard unit price considering overall factors that affect the construction work unit price, such as the finishing materials level, structure, basement availability, and landscaping & site civil work

2.2 Calculation of additional elements

* Note: Construction costs need to be estimated generously with consideration of surcharge because the project will be launched 3 to 5 years later

3. Estimated architectural part costs

3.1 Calculating construction costs (A) * Note: Estimated gross total floor area * X Construction unit price

3.2 Architectural design service fees (B) * Note: Include general expenses needed in the design phase

| Item | Average unit price |
| --- | --- |
| Design costs | Total construction costs USD 3,744,400 × % = USD |
| Permission and approval fees | USD 60,000 |
| Topographic surveying and geological survey expenses | USD 30,000 |
| Total (estimated design costs) | USD 371,494 |

3.3 Construction management (CM) service fees (C) * Note: Estimate CM fees within the range of 7–10% of the construction costs

3.4 Local supervision service fees (D) * Note: Estimate locally feasible supervision fees

3.5 Contingency fund (E) * Note: Reserved to respond to design changes during construction work or additional requests from the recipient; around 5% needs to be applied for new construction work, and more than 10% needs to be applied for extension or renovation

Ⅶ. Time schedule of project implementation

1. Time schedule of project implementation (draft)

| Classification | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1/4 |  |  | 2/4 |  |  | 3/4 |  |  | 4/4 |  |  | 1/4 |  |  |  | 2/4 |  |  |  | 3/4 |  |  |  | 4/4 |  |  |  | 1/4 |  |  |  | 2/4 |  |  |  | 3/4 |  |  |  | 4/4 |  |  |  | 1/4 |  |  |  | 2/4 |  |  |  | 3/4 |  |  |  | 4/4 |  |  |  |
| Design bidding and Contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction bidding and contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commencement and completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Handover and defects liability period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

2. Design period (XX months)

A. Design bidding and Contract (XX months) * Note: A sufficient period needs to be reflected, considering KOICA’s standard bidding plan establishment—announcement—bid conference—technical evaluation—opening of the bid—estimated total period for design contract (at least 3 months)

B. Design (XX months) * Note: The design period also needs to include the design review and approval periods

2. Construction period

A. Construction bidding and contract

B. Commencement and completion

3. Handover and Defect liability period

* Note: Usually, the warranty is set to 2 years for KOICA projects; however, it can be reduced to 1 year depending on local laws

Ⅷ. Risk factors and countermeasures

1. Planning phase

| Risk factor | Possibility of occurrence | Impact | Countermeasures |
| --- | --- | --- | --- |
| Change of project details and scope | High / Med / Low (select one) | High / Med / Low (select one) | - Clearly confirm the project details and scope based on detailed survey on the project conditions as well as specific and sufficient consultation between the parties concerned |

2. Design bidding and design phase

| Risk factor | Possibility of occurrence | Impact | Countermeasures |
| --- | --- | --- | --- |
| Insufficient reflection of special items: Various facilities related to the laboratory, demolition work, renovation work | High / Med / Low (select one) | High / Med / Low (select one) | - Reflect experience in laboratory design and renovation work design in the service provider selection criteria |

3. Construction bidding and construction phase

| Risk factor | Possibility of occurrence | Impact | Countermeasures |
| --- | --- | --- | --- |
|  | High / Med / Low (select one) | High / Med / Low (select one) |  |

4. Completion and O&M phase

| Risk factor | Possibility of occurrence | Impact | Countermeasures |
| --- | --- | --- | --- |
|  | High / Med / Low (select one) | High / Med / Low (select one) |  |

Appendix 1 - Checklist

Architectural part report checklist (report writer)

| Survey phase | Architectural survey v.1 | Architectural survey v.2 |  | Architectural survey v.3 | Architectural survey v.4 |
| --- | --- | --- | --- | --- | --- |
| Classification | Item (standard of judgment) |  | Response |  |  |
| Ⅰ. Proposed project site | 1. Legal ownership of the site (Land boundaries, ownership, existing building status, necessity of relocation and removal) |  | Checked Additional check required |  |  |
|  |  |  | The site is owned by the government and will be designated as a site managed by the recipient (MoE) in 2020. |  |  |
|  | 2. Analysis of infrastructure status (Water supply, power supply, sewage treatment method, telecommunications and Internet connection, etc.) |  | Checked Additional check required |  |  |
|  |  |  | Refer to the table on p. 23. Additional power supply is needed. |  |  |
|  | 3. Accessibility to the project site (Width and pavement conditions of the access road, vehicle access conditions, status of public transportation, etc.) |  | Checked Additional check required |  |  |
|  |  |  | The recipient will conduct road expansion work within 2020. |  |  |
|  | 4. Status of site and surrounding facilities (Land shape, topographic analysis (elevation difference), ground conditions, nearby hazardous facilities, etc.) |  | Checked Additional check required |  |  |
|  |  |  | Related facilities are located near the target site. |  |  |
|  | 5. Possibility of extension and expansion (Whether the possibility of future extension is considered, and site for extension is available or not) |  | Checked Additional check required |  |  |
|  |  |  | Currently not considered. If extension is needed, the surrounding site needs to be secured. |  |  |
|  | 6. Relevant laws and constraints (Constraints imposed by laws and regulations, such as those related to urban planning, buildings, fire services, environment) |  | Checked Additional check required |  |  |
|  |  |  | Building-to-land ratio, floor area ratio, floor limit, etc. |  |  |
|  | 7. Optimality of the site among multiple sites (If there are +2 candidate sites, select a site considering each item of the above conditions) |  | N/A +2 candidate sites Other (multiple sites) |  |  |
| Ⅱ. Architectural plan and review | 1. New construction, extension, or renovation status, and planned scope (Detailed description of various construction activities needed, such as new construction, extension, renovation, and use change) |  | New construction Extension (area increase) Renovation (area unchanged) |  |  |
|  |  |  | Both new construction and extension of an existing building |  |  |
|  | 2. Appropriateness of space program (Discuss the number of beds, medical departments, and number of operating rooms for the hospital, and discuss the number of students, subject type, number of teachers, special classrooms, etc. for the school) |  | Consulted with survey team Consulted with recipient Other |  |  |
|  |  |  | Total floor area: ㅇㅇㅇ m2; Buildings: ㅇ |  |  |
|  | 3. Reflection of public space (Reflect appropriate public space considering the program and climate environment) |  | +30% of public space Less than 30% of public space |  |  |
|  |  |  | Reflected more than 40% of public space considering local school facilities and reflected 30% for the dormitories |  |  |
|  | 4. Assignment of each party (Consider specific matters, such as geological survey, topographic surveying, auxiliary site civil work, fences/walls, emergency generator, roads on premises, and signs) |  | Standard plan reflected Workload readjusted |  |  |
| Ⅲ. Calculation of architectural part costs and procurement plan | Total architectural project costs: USD 000 |  |  |  |  |
|  | 1. Unit price of construction costs (Comprehensively consider the use of the building, structure type, finishing level, ground condition, basement availability, etc.) |  | Applied unit price of less than USD 500/m2 Applied unit price of USD 500–1,000/m2 Applied unit price of USD 1,000–1,500/m2 Applied unit price of more than USD 1,500/m2 |  |  |
|  |  |  | Applied unit price: USD 000/m2 |  |  |
|  | 2. Constructor selection method and matters to consider when calculating the unit price of construction costs (Total floor area × Unit price of construction costs (USD/m2) + Construction cost for other than buildings (e.g. site civil work engineering, landscaping) + Additional items. Take into consideration factors such as surcharge, inflation, and VAT.) |  | Domestic bidding Local bidding Other (consignment to international organization, using the recipient's system, etc.) |  |  |
|  |  |  | Inflation rate reflected Inflation rate not reflected |  |  |
|  |  |  | Other construction costs included Other construction costs not included |  |  |
|  |  |  | VAT included VAT exemption |  |  |
|  |  |  | Construction costs: 000 USD reflected |  |  |
|  | 3. Considerations about design firm selection method and design costs (Although geological survey data of the recipient is available, during the design phase, the data needs to be checked additionally) |  | Korean architect selected Local architect selected Package bidding of design and construction Other (architect selection not required) |  |  |
|  |  |  | (Check only when a Korean architect is selected) Local travel expenses considered Local subcontracting considered |  |  |
|  |  |  | Geological survey and survey costs reflected Survey costs not reflected |  |  |
|  |  |  | Design costs: Construction costs × 00%, USD 000 reflected |  |  |
|  | 4. CM selection and costs (Recommended to apply 7–10% of the construction cost; consider 10% for construction costs of USD 2 million or more, 8% for USD 2–5 million, and 7% for USD 5 million or more) |  | Local CM CM selection required |  |  |
|  |  |  | CM costs: Construction costs × 00%, USD 000 reflected |  |  |
|  | 5. Local supervision and calculation of service fees (Apply 4–5% of construction costs) |  | Local supervisor Local supervisor not required |  |  |
|  |  |  | Local supervision fees: Construction costs × 00%, USD 000 reflected |  |  |
|  | 6. Reserve fund for construction work (Prepare as a separate budget item of the construction cost; apply around 5% of construction costs for new construction and around 10% for extension and renovation) |  | Reserve fund reflected Reserve fund not reflected |  |  |
|  |  |  | Reserve fund: Construction costs × 00%, USD 000 reflected |  |  |
| Ⅳ. Calculation of project period | 1. Design company selection and design period (Selection period: 3 months; calculate the design period including the permission and approval obtainment period) |  | Less than 6-month design period More than 6-month design period |  |  |
|  |  |  | Procurement preparation and selection period: 00 months; Design period: 00 months |  |  |
|  | 2.Constructor selection and construction period (Selection period: 4–6 months; calculate the construction period considering the period that affects construction work, such as trial operation, permission and approval of construction completion, rainy season, etc.) |  | Less than 12-month construction work period More than 12-month construction work period |  |  |
|  |  |  | Procurement preparation and selection period: 00 months; Construction work period: 00 months |  |  |
|  | 3. Warranty (Calculate the period considering KOICA's regulations and local standards) |  | 24 months 12 months Other |  |  |
|  |  |  | Local regulations applied |  |  |

Appendix 2 – Other documents (Construction unit price data, cadastral map, drawing, brochure, etc.)