KOICA

August 2020

Guidelines for Architectural Part Survey Report

Review of project site

1

A. Selecting an appropriate project site

◆ A site for the project including building facilities should be carefully selected because the selected site has an absolute influence on the project's performance and sustainable operation during and after project implementation.

◆ An optimal site should be selected after analyzing alternative (multiple) project sites proposed by the recipient according to the review criteria.

- Review the appropriateness of site conditions, such as land area, infrastructure and topography conditions, as well as the appropriateness of physical land conditions regarding factors for sustainable operation.

- Review the appropriateness of the geographical location regarding easy accessibility to the facility to be established, modes of transportation and mutual proximity with local communities.

※ Note: If the survey results of the site proposed by the recipient seems to be inappropriate, active consultation with recipient is needed for them to propose alternative site best suitable for the project.

B. Items to be checked in site selection and review

◆ Project site information

- Address of the project site (Check administrative jurisdiction)

- Check aerial photographs and maps

: Review and analyze the wide area of the project site, using aerial photographs and maps to check facilities in neighboring areas, internal accessibility of the site, and proximity to major facilities in downtown

- Check relevant laws and regulations of the project site area, such as those related to urban planning, buildings, environment, fire services, altitude limit, cultural heritage management, medical facilities (if necessary)

- Land registration map and topographic survey drawing

: As land registration data is needed to check the physical conditions of the project site, such as the site area, shape, topology, elevation and obstacles, request the data to the recipient's person in charge; if the data is not available, the accurate land boundary should be checked by asking the recipient's person in charge

- Land ownership and ownership of existing buildings

: Check whether there is any hindrance to the start of the project by contacting the landowner; if there is an existing building in the site, check whether it will be demolished, left intact or relocated, and how the necessary costs will be covered

◆ Status of surrounding area and relationship with surrounding facilities

- Check the environment, heritage preservation areas and facilities around the project site

- Check for interconnected functions in relation to neighboring facilities

- Check whether there is any infrastructure shared with adjacent buildings in common

- Check whether there is a possibility that a nearby building can cause harmful factors, such noise and pollution, and whether there is any hindrance when implementing the project

※ Note: When an additional facility is provided to existing facilities in the recipient country, such as hospitals and schools, it is necessary to check the interconnected functions and infrastructure conditions because they may be linked with facilities in the existing complex

(e.g. interconnected operation, central supply, and treatment facility of the existing building should be considered when new hospital inpatient ward is provided.)

◆ Accessibility to project site

- Accessibility from the city center, mode of transportation, ease of walking and driving, etc.

- Status of public transportation, and traveling distance and frequency

- Width and pavement conditions of the front road

※ Note: It is desirable to secure at least two lanes (8 meters) for roads connected to the main entrance of the project site and the road surface should be smoothly paved, and separate pedestrian walkways should be installed on the sides of the vehicle road for safe accessibility to the facility

◆ Analysis of the infrastructure status

- Conduct a survey on the present conditions of the infrastructure to be connected to the project site with a focus on facts based on survey data and interviews with government officials, etc., rather than assumption

- Accurate information should be obtained, such as the current installation status of infrastructure in the project site or nearby, the extension plan in case no such infrastructure, and contact information of the department in charge.

| Classification |  | Requirement | Details |
| --- | --- | --- | --- |
| General architecture | Water supply | ✔ | - Check whether water can be supplied stably - Consider alternative methods (e.g. deep-well development, water purchase) if not available |
|  | Rainwater treatment | ✔ | - An area installed with rainwater drainage pipes is recommended for facilities in downtown - Review the environment and influence of surrounding areas for natural drainage treatment |
|  | Sewage treatment | ✔ | - Plan rainwater drain piping and sewage piping separately as much as possible - Include plan for septic tank installation if there is no sewage treatment pipe |
|  | Power supply | ✔ | - Check for stable power supply - Consider alternative methods (e.g. solar photovoltatic generation, power generator) if not available |
|  | Heat source |  | - Check the types of main heat sources (e.g. gas, oil) and review the plan for necessary facilities |
| Hospital (further review) | Medical gas |  | - Check whether it is a central supply or a mobile type |
|  | Water quality | ✔ | - Check whether there is any lime or other contaminants (causes of medical equipment failure) |
|  | Incinerator |  | - Check the method of medical waste incineration - Include plan for a separate incineration facility if not available |
|  | Wastewater treatment |  | - Separate plan needed for medical wastewater piping and collecting well |

◆ Check climate and disaster safety

- Check the extent of the flood damage during the rainy season, and check whether the site is an area prone to flooding due to its location in the lowland

- Check the safety of retaining walls at the boundary of surrounding sites

- Consider rainwater inflow and soil erosion to the project side due to the level difference in the entrance road and site

- Check the site's accessibility by fire trucks

◆ Possibility of facility expansion in the future

- Secure spare space enough for horizontal expansion considering future facility expansion due to subsequent projects and necessity for facility operation

- The future extension site must be considered for medical facilities

◆ Matters to consider for repairs and extension/renovation

- For vertical extension, check the strength of the existing structure to check the possibility of extension

- For horizontal extension, review the scope of work sharing for demolition and connection of the extension joint part, and the construction plan

- Extensions and renovations must include at least 10% of the reserve fund in the construction work budget

Space program and basic plan

2

A. Decision of execution plan

◆ Finally decide the project execution plan: New construction; Extension; Renovation (Remodeling)

- (New construction) Most of the projects are new construction; review according to the general guidelines of architectural part survey, considering the selected site and its conditions

- (Extension) A method of increasing the area of the existing building in the horizontal or vertical direction, or securing functional connection with the existing building by constructing a separate building. A survey on the present conditions and spatial function analysis of the existing building must be conducted at the same time

- (Renovation/Remodeling) A method of remodeling or repairing the existing old building; compared to new construction, the effect of reducing the burden of construction project management and reducing costs can be expected—however, preliminary close investigation is required because project management efforts and required costs may be increased to a large extent due to the level of aging, additional installation of machinery and electrical system, and construction work conditions during facility operation

※ Note (for renovations): Sometimes, the project of extending or renovating the existing building is planned for the purpose of reducing the cost of the project and administrative work—however, the extent of management may increase from the perspective of construction work, because renovation costs more than new construction depending on the aging of the existing building and level of additional construction, and extension work at the same time, such as demolition and reinforcement of aged parts and electrical work. Therefore, a well-thought-out survey must be conducted in the planning phase for the extension and renovation type construction project, including a preliminary survey cost of the existing building, and the reserve fund of 10–15% or more, etc.

※ Note (for small-scale and multiple building constructions): If a project is designed to construct many small-scale and simple buildings in several areas with similar programs, there is much more difficulties and management costs in terms of project management compared to the simplicity of each construction work—therefore, elaborate pre-arranged plans are required, such as project implementor selection, CM management method, and assessment of the existing site. As a result, it is recommended to avoid this type of projects as much as possible.

B. Finalization of the space program

◆ Finalize the building space program through detailed review of the purpose of construction, required room space and the number of rooms, size, capacity, etc.

- Consult and check the number of people to be occupied in the building, required architectural space, etc., according to the recipient's request

- Calculate the final total floor area through discussion with the survey group, such as operation program, required space, area, etc.

Example 1) Hospital - Number of beds, outpatients, operating rooms, delivery rooms, treatment rooms and medical personnel, as well as hospital operation plan (food, laundry, medical gas, etc.)

Example 2) School - Number of students, courses, classrooms, teachers, teaching materials and equipment, , etc.

Example 3) Dormitory - Number of persons to be accommodated, , gender ratio, persons per room, meal service plan, scope of internal furniture supply, etc.

- The space program should include the public space, such as corridors, stairs, rooms and electrical/machinery rooms. after determining the assigned space according to the above program; public space should be secured in consideration of gallery-type corridor of which one side faces the open air, rather than compact arrangement of a double-loaded corridor type

※ Note: The ratio of public space should be at least 30–35% of the total floor area

◆ Scope of construction work to be carried out by KOICA

- Set the scope of KOICA’s construction work, which becomes the criteria of estimated construction costs, ranging from buildings to subsidiary work and annex facilities

- It differs depending on the scope of sharing work of the construction project that will be stated in the RoD; all items that can cause an increase in construction costs should be reflected to prevent the omission of the budget item

- If KOICA needs to undertake site civil works, landscaping, fence, gate, emergency generator, septic tank, water tank, and waste disposal site, it should be reflected in the construction costs

※ Note: There should be no missing items in construction cost estimation which shall include the facilities that should be installed outdoor as an annex to the main building, such as the elevated water tank, outdoor septic tank, incineration plant, waste treatment plant, guard house, etc.

◆ Example of the space program

| Classification | Rooms | Room area (m2) | Quantity | Total area (m2) | Remarks |
| --- | --- | --- | --- | --- | --- |
| Administrative | Admin. Office | 60 | 1 | 60 |  |
|  | Archives, Storage, Pantry | 20 | 1 | 20 |  |
|  | Meeting Room | 60 | 1 | 60 |  |
|  | Principal’s Room | 40 | 1 | 40 | 1-person |
|  | Vice Principal’s Room | 20 | 1 | 20 | 1-person |
|  | Reception | 20 | 1 | 20 | Including pantry |
| Subtotal |  |  |  | 220 |  |
| Educational | Instructor’s Room | 60 | 1 | 60 | 0-person |
|  | Waiting Room | 20 | 1 | 20 | For visiting instructors |
|  | Classroom | 40 | 6 | 240 | 6 (30-person rooms) |
|  | Reference Room | 40 | 1 | 40 | Including archives |
|  | Rest Room | 20 | 8 | 160 | 8 (10-person rooms) |
|  | Audiovisual Room | 40 | 2 | 80 |  |
| Subtotal |  |  |  | 600 |  |
| Public | Exhibition Hall | 40 | 1 | 40 |  |
|  | Night-duty Room | 20 | 1 | 20 | 1-person |
|  | Storage | 20 | 1 | 20 |  |
|  | Auditorium | 360 | 1 | 360 | 250-person (including stage, storage, control room, waiting room) |
|  | Cafeteria | 180 | 1 | 180 | 120-person (for students and faculty) |
|  | Kitchen | 40 | 1 | 40 | Cafeteria (including kitchen, storage) |
| Subtotal |  |  |  | 660 |  |
| Dormitory | Student Dorms | 25 | 25 | 625 | 4-person rooms for 100 students (including bathroom, balcony, cabinets) |
|  | Faculty Dorms & Guest Rooms | 60 | 4 | 240 | 3-person rooms for 12 instructors (including bathroom, balcony, cabinets) |
|  | VIP Dorms | 60 | 2 | 120 | 2 rooms |
|  | Lounge | 40 | 2 | 80 |  |
|  | Kitchenette | 40 | 2 | 80 |  |
|  | Laundry | 40 | 2 | 80 |  |
|  | Storage | 20 | 2 | 40 |  |
| Subtotal |  |  |  | 1,265 |  |
| Etc. | Machinery Room, Electrical Room | 100 | 2 | 200 | Including service room |
|  | Main Gate & Guard House | 30 | 1 | 30 | Including bathroom |
|  | Elevated Water Tank | 20 | 2 | 40 | New |
|  | Substation | 10 | 2 | 20 | New |
| Subtotal |  |  |  | 290 |  |
| Total area of assigned space |  | 3,035 |  |  |  |
| Total area of public space |  | 1,665 |  |  | Lobby, bathrooms, corridors, stairs, passageways, etc. |
| Total floor area |  | 4,700 |  |  |  |

C. Secondary review of the space program

◆ The space program should be finally confirmed after deep consideration of budget and adjustment of required floor area, because the total floor area coming from the space program becomes the basic element for estimating the entire project cost as well as construction cost

- If the total project architectural part cost is estimated more than the relevant budget, return to the space program review phase, and discuss the way to reduce the cost (reducing the floor area, lowering the quality, or others) and proper supplementation is required.

- Adjusting the total floor area to simply fit into the construction budget limit (reducing the ratio of public space, allocating an inappropriate room area, etc.) must be avoided

D. Proposing matters to consider in architectural planning and design

◆ Describe functional and environmental considerations that should be reflected in the construction because it becomes the basic contents of the design proposal request document and design guidelines

Calculation of architectural part costs (A + B + C + D + E)

3

A. Composition of architectural part costs

| Classification |  | Calculation |  | Basis |
| --- | --- | --- | --- | --- |
| Construction costs (A) = ⓵ + ⓶ (⓶ = ⓵ × 10–15%) |  | ⓵ Total floor area (construction) × unit price (USD/m²) ⓶ Incidental expenses (landscaping, roads on premises, auxiliary site civil work) |  | - Survey the actual construction cost of local buildings - Should determine the unit price considering the final quality of the building to be built (first refer to cases of other aid organizations and public procurements, etc.) - Should consider the extent of the increase in the construction work unit price due to fluctuations in inflation when construction work starts after 3 to 5 years, considering the start date of construction work - Review VAT exemption and refund methods in advance |
| Service fees | Design (B) | Local company | (A) × about 4–7% | - Should calculate design costs as a total amount compared to the construction costs - Local geotechnical investigation and topographic surveying expenses should be included |
|  | CM (C) | (A) × about 8–10% |  | - Should be classified into domestic-inside Korea (non-resident) and overseas-outside Korea (resident CM and non-resident group’s business travel) - Should consist of personnel expenses, overhead expenses, technical fees, and direct expenses |
|  | Supervision (D) | (A) × about 5% |  | - Usually estimated and contracted as a total amount |
| Contingency (E) |  | (A) × about 5–10% |  | - Reserved in case of design changes and force majeure costs |

B. Calculating the unit price of construction cost (USD/m2)

◆ Level of the building to be provided

- Set the level of factors that can affect the unit price of construction costs, such as building size, finishing materials level, main framework, basement availability, and scope of landscaping, etc.

(Example) ○ Total floor area: 4,755 m2 / 3 floors / Secondary hospital for mothers and infants / Construction period: 2013–2014 ○ The finishing materials and equipment of the hospital is the intermediate level of the national and private hospital ○ Main finishing materials (equal or higher) - Floor finishing materials: Ceramic tile or granite tile; Functional room-vinyl sheet - Wall finishing materials: Acrylic paint - Ceiling finishing materials: Sound absorbing soft fiber board - Windows and doors: Aluminum windows; Wooden doors - Installing an air conditioner in all rooms except for the public space

◆ Survey the proper unit price of the past construction work (see Attachment 1)

- If 'standard of construction estimate', and material price and labor rate published by government approved organization are not available in the country, building construction work cost should be estimated based on the past construction cost reference.

- Survey the construction costs of 3 to 4 projects of which usage and quality level is similar to the target building.

- Review the cases of the construction projects supported by the aid organization or international NGO with similar conditions to Korea (e.g. JICA, UNOPS, INGO), or refer to the cases of the projects supported by Korean ODA

- Calculate the amount affected form the inflation arising from the time difference between the surveyed project construction year and the year of target new construction, also consider the cost increase coming from difference of the conditions.

- Analyze the factors that can affect an increase in construction costs such as the inflation rate of the last 3 to 5 years, fluctuations in exchange rates, and circumstances of major materials importing countries, reflect them in the unit construction cost

- It is necessary to reflect additional amounts such as safety management cost (more than 0.5% of the net construction cost) in construction costs

- It is necessity to estimate the final amount so that the construction budget amount can be estimated that is enough to place an order for the start of construction work, based on the surveyed construction costs

※ Note: The survey through a recipient or local company tends to present the construction cost of general building of which unit price is rather low; if the unit price of construction costs is set low, the budget may be insufficient at the project implementation phase—therefore, it is desirable to check the construction costs of relatively high quality and recently built buildings or among projects that were built by aid organization

※ Note: The estimated unit price of the construction cost needs to reflect the inflation for 3 to 5 years (construction phase) and the inflation rate to be average of recent 5 years.

C. Calculating construction costs (A)

◆ Construction costs = ① [Total floor area (m2) × unit price (USD/m2)] ② Incidental expenses (landscaping, roads on premises, site civil work)

- ① The total construction costs is calculated from the total floor area of the space program which is multiplied by the construction unit price.

- ② Confirm the scope of the project according to the recipient's work scope of the expected RoD, and include the amount of outdoor ancillary buildings construction work and site civil work to the construction costs

◆ As it is difficult to estimate the construction cost per unit area for extension, remodeling, renovation and repair projects, the unit price of construction cost of each construction work type should be separately reviewed, which reflects the characteristics of each type of construction.

◆ Check the VAT exemption and refund method of the recipient organization and reflect it in the construction costs

※ Note: If VAT exemption is not possible, VAT should be included in the construction contract amount, as the VAT of developing countries is about 15 %, relatively high on average, which affects the estimated budget amount and construction quality, the advance assessment of the VAT is needed (check with the office)

D. Architectural design service fee (B)

◆ Calculating the design service fee when local design company is to be selected

: ① (Construction costs A × 3–5%) ② (Geological survey, topographic survey fee)

- ① Calculate the design fee according to the design cost rate based on the local building act or local business practices (generally, it is around 5% of the construction costs)

- ② Geological survey and topographic survey fee should be included in the design service fee

E. Construction management (CM) service fee (C)

◆ A project with less than USD 10 million construction cost belongs to the regional (Korean) CM project, and the construction project management cost should be set within 7–10% of the construction costs

- If a manager should be an on-site resident due to the scale and difficulty of construction work, dispatching the resident CM to the country, which occurs various expenses should be reflected in the CM budget

※ Note: Consider the CM fee, 10% for construction costs of less than USD 2 million, 8% for USD 2–5 million, and 7% for USD 5 million or more

◆ A project CM should be appointed for a project with more than USD 10 million total construction costs—the budget should be estimated in consideration of the assignment and stay period of the resident and non-resident personnel for practical project management

- In case of large scale project, continuity of construction management and resident CM is necessary, thus separate CM is selected other than regional CM. Apart from the resident CM, the nonresident specialists at CM company head office in each specific field are required, and head office manager is also required to be provided. These all factors need to be reflected in the budget.

- In addition, the cost of hiring local engineers to assist as to local construction conditions and to support resident CM should be reflected

※ Note: Generally, whether to appoint a single project CM or use a regional CM is determined by the construction amount of USD 10 million—however, it can differ by reviewing effectiveness according to the characteristics of the project, it should be determined by consulting with the construction officer in the main office regarding the management method

F. Local supervision fees (D)

◆ Calculating the design service fees, in case that local supervision company is utilized.

: Construction cost (A) × about 4–5%

- Calculate the supervision service fees according to the rate of supervision fees based on local building laws or local business practices

- Calculate the local supervision fees separately, besides the regional CM budget, for the construction project of the country that requires mandatory local supervision for each project according to regulations and laws of the country

※ Note: Countries in Africa, Latin America, and Middle East require local supervision due to business practices and laws

G. Contingency in the Construction budget (E)

◆ Contingency: Construction cost (A) × about 5–10%

- An amount prepared for various unpredictable matters that may occur in overseas construction projects—this amount needs to be included in the construction project cost, apart from the project management cost in budget.

※ Note: Secure 5% or more of the contingency for new constructions and 10% or more for the extensions and renovations

Procurement plan

4

A. Review of the design company selection method

◆Design company selection method

① Local design company bidding

- If local supervision is needed, sometimes, the design and supervision both are included in a contract agreement.

- Describe how to select a local design company. (bidding, public contest, etc.)

② Design build bidding

- When selecting a contractor, including design services in his construction work.

- This method is advantageous if the initial design guidelines and construction scope are exactly defined—however, if there are many stakeholders like KOICA project, and mediation of interests occurs frequently while implementing the project, such as material and equipment, recipient country’s requirements, etc., architectural design quality may deteriorate, or designs needs to be changed frequently. Therefore, the method should be selected according to the nature of the project

B. Review of the local supervision selection method

◆ If a country requires local supervision, include local supervision selection in the plan in the construction or design phase

C. Review of the constructor selection method

◆ Review the method of selecting a constructor by the local public institute—it is necessary to describe local information, such as bid bond, performance guaranty bond, guaranty ratios defect liability period, etc.

Schedule plan of project implementation

5

A. Schedule plan of project implementation

◆ Plan the construction project implementation schedule by including the following five phases in the entire project

- ① Design bidding and contract → ② Design → ③ Construction bidding and contract → ④ Start and completion of construction → ⑤ Handover and defect liability

| Classification | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1/4 |  |  | 2/4 |  |  | 3/4 |  |  | 4/4 |  |  | 1/4 |  |  | 2/4 |  |  | 3/4 |  |  | 4/4 |  |  | 1/4 |  |  | 2/4 |  |  | 3/4 |  |  | 4/4 |  |  | 1/4 |  |  | 2/4 |  |  | 3/4 |  |  | 4/4 |  |  |
| Design bidding and contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Architectural design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction bidding and contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start and completion of construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Handover and defects liability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Warranty (2) |  |  |  |  |

- 1 month for bidding preparation, 1.5 months for bidding announcement and bid document receipt, 0.5 month for technical negotiation and contract

C. Design

◆ The period required for actual design, permission and approval obtaining period, design review period by CM should be considered together

- Undertaking survey (0.5 month) + Planning and basic design (3 months) + Basic design drawings and documents review (0.5 month) + Detailed(or construction) design (3 months) + Detailed(or construction) design drawings review and approval (1 month)

- If construction drawings and documents should be prepared both in Spanish and English as in Latin America, estimate the period including the additional design period required for drawings and documents translation

※ Note: If a contract agreement is made while the practical design service period is set improperly, a dispute over the delivery delay of the design company and delay penalty may occur—therefore, it is necessary to set an appropriate service period considering the difficulties of overseas architectural design services

D. Construction bidding and contract

◆ A period required from planning a construction bidding to final contract agreement after design completion (it takes 4–6 months on average)

- 2 months for bidding preparation and prior consultation, 2 months for bidding announcement and bid document evaluation, 1-2 months for winner selection and conclusion of contract agreement / 1 more month if pre-qualification (PQ) is performed

- Scheduling by overlapping the design phase and the construction bidding preparation period (2 months) is allowed to reduce the construction bidding period

※ Note: There are many project cases that actual project construction contract was delayed due to the estimation of less than 3 months for construction bidding and contract agreement, which subsequently delayed the entire project, results in inevitable changes in PMC, materials and equipment, CM, and supervision period

E. Construction and completion

◆ A proper construction period should be estimated by considering all of various factors without omission, such as construction work conditions in the rainy season, construction materials import, and period required for tax-free

◆ As the distance of the construction site from the large city affects the construction capability and construction period, an additional construction period should be considered if the project site is located in the remote area from the large city.

◆ When estimating the construction period, completion of construction, and test on completion (construction completion permit), and commissioning test period should be included

※ Note: If the project includes construction work, the construction period frequently affects the project implementation plan, installation of furniture and equipment, and construction period of other services—therefore, realistic construction implementation plan should be reflected when planning the project period in the initial phase

F. Handover and defect liability warranty

◆ The project implementation period of architectural part should include the transfer of facilities to the recipient institute after construction completion, and the guarantee period of defect liability securities after construction completion by the constructor

- “Procurement and agreement regulations for foreign aid cooperation projects” stipulate that the warranty period for construction agreement should be more than 2 years—however, it can be reduced to 1 year depending on local procurement regulations or laws

Confirmation of commitments by both participants in record of discussion (RoD; RD)

6

A. Commitments by both participants for construction in RoD

◆ The RoD issued during the implementation discussion should describe the work scope of each country with regard to construction works. The list stating work scope needs to be attached to the RoD, by which the detailed work scope of each country is clearly defined.

◆ The table below shows the detailed scope of each party; KOICA provides the design, supervision, and construction of the building and site civil work, whereas the recipient provides data related to the project site, perform land preparation of the site before the start of construction, intake of various infrastructure, and duties about permission and approval, and tax-free provisions.

◆ Commitments by both participants for construction (example)

| Classification | Details | Standard work |  |  |
| --- | --- | --- | --- | --- |
|  |  | KOICA | Recipient/timeframe |  |
| Site survey and data collection | Geotechnical investigation report Conducting geological survey | ○ |  |  |
|  | Boundary and topographical survey Conducting reconnaissance survey | ○ |  |  |
|  | Providing cadastral survey map of site |  | ○ | When selecting a site |
|  | Providing existing facility site plan Providing the arrangement plan of existing facilities |  | ○ |  |
| Removal of existing buildings | Demolition |  | ○ | During the design phase (before construction begins) |
|  | Demolition costs |  | ○ |  |
|  | Handling after demolition |  | ○ |  |
| Paving for roads and Site clearance | Installment and pavement of access roads |  | ○ | Design phase (before construction begins) |
|  | Site clearance |  | ○ |  |
| Infrastructure facilities | Water supply intake |  | ○ | Start of construction/ construction phase |
|  | Sewage and rainwater facility intake |  | ○ |  |
|  | Power intake |  | ○ |  |
|  | Telecommunications and Internet connection |  | ○ |  |
|  | Heat source supply |  | ○ |  |
|  | Waste disposal |  | ○ |  |
| Architecture | Design and construction | ○ |  |  |
|  | Supervision / CM | ○ |  |  |
|  | Fences (walls) | ○ |  |  |
|  | Main entrance | ○ |  |  |
|  | Landscaping, auxiliary civil engineering (elevated water tank, septic tank, etc.) | ○ |  |  |
|  | Emergency generator | ○ |  |  |
|  | Inner roads and pedestrian roads | ○ |  |  |
|  | Internal and external signs | ○ |  |  |
| Building permits | Permission and approval | (○) | ○ | During design phase, upon completion |
|  | Cooperation for permission and approval |  | ○ |  |
|  | Expenses for permission and approval | (○) | ○ |  |
| Tax exemptions | Duty |  | ○ | Upon occurrence |
|  | VAT |  | ○ |  |
| Cooperation for material transportation |  |  | ○ | Upon occurrence |

- Tasks in yellow color will be carried out by KOICA

※ Note: The above table is a standard draft, and detailed contents can be adjusted by project circumstances and discussion with the recipient

[Attachment-1] Construction work unit price data of KOICA architectural projects

※ Unit construction cost are classified into “Constructed (Complete)”, “Construction phase (◎)”, “Survey and pre-order phase (△)” by project implementation phase

※ A conversion amount for the construction agreement amount; should be reflected considering the successful bid rate and inflation rate when calculating the project budget

| Country | Project name | Total floor area (m2) | Unit construction cost (USD) | Type | Phase |
| --- | --- | --- | --- | --- | --- |
| Cambodia | Project for the Capacity-Building of Civil Aviation Management and the Establishment of a Training Center in Cambodia (2013-2017 / USD 1.01m) | 2,827 | 1,189 | New construction | ◎ |
|  | Project for the Functional Improvement of the National Children's Hospital in Cambodia (2013-2018 / USD 7.28m) | 6,142 | 697 | Remodeling | ◎ |
|  | Project for the Capacity-Building of the Ear-Nose-Throat Department (ENT) of Preah Ang Doung Hospital in Cambodia (2018-2022 / USD 8m) | 4020 | 1,000 | New construction | ◎ |
|  | Project for the Establishment of an Industry-Academia Business Incubation System in Cambodia (2019-2023 / USD 7m) | 1600 | 1250 | New construction | △ |
|  | MCH Program for Isolated Areas in Northeast Cambodia (2019-2023 / USD 7m) | 954 | 600 | Local construction method | △ |
|  | Project for Rural Community Development in Cambodia (2014-2018 / USD 8m) | 2,780 | 941 | New construction | ◎ |
|  | Project for the Capacity-Building of Batheay Referral Hospital in Cambodia (2011-2014 / USD 3.5m) | 3,127 | 729 | New construction | ◎ |
|  | Project for the Establishment of an Eye-Specialized Hospital in Cambodia (2011-2014 / USD 5.5m) | 3,200 | 962 | New construction | ◎ |
| Laos | Project for Integrated Maternal Neonatal Child Health Care on Pediatrics Education (I-HOPE) in Laos (2013-2019 / USD 9.5m) | 1,926 | 748 | New construction | ◎ |
|  | Project for Rural Community Development in Laos (2014-2019 / USD 14.55m) | 2,742 | 817 | New construction | ◎ |
|  | Project for the Empowerment and Capacity-Building of Souphanouvong University in Laos (2014-2017 / USD 3m) | 25,294 | 600 | Remodeling | ◎ |
|  | Project for the Establishment of a School for Minority Ethnic Groups in Vang Vieng, Laos (2008-2011 / USD 5.68m) | 675 | 431 | Local construction method | ◎ |
|  | Project for the Capacity-Building of an IT Center for the Youth Union in Laos (2016-2019 / USD 3m) | 1,450 | 850 | New construction | ◎ |
|  | Project for the Administrative Capacity-Building for Immigration Control in Laos (2017-2021 / USD 8.6m) | 5675 | 1000 | New construction | ◎ |
|  | Project for the Capacity-Building of Korea-Laos Vocational Development Institute in Laos (2017 - 2021 / USD 5.85m) | 2200 | 600 | New construction + Remodeling | ◎ |
|  | Project for the Strengthening of Services and Developing Local Programs to Improve Access to Sexual and Reproductive MHC in Laos (2019-2024 / USD 7.5m) | 1000 | 500 | Local construction method | △ |
|  | Integrated Program for the Strengthening of Resilience and Self-Reliance to Respond to Climate Change in Attapeu Province, Laos (2019-2023 / USD 11.5m) | 2000 | 650 | Local construction method | △ |
| Myanmar | Project for Farmland Reorganization and Agricultural Machinery Training for Agricultural Industrialization (2013-2016 / USD 6m) | 3,353 | 582 | New construction | ◎ |
|  | Project for the Establishment of a Research Institute for Management Crops After Harvesting in Myanmar (2014-2017 / USD 4.5m) | 2,100 | 818 | New construction | ◎ |
|  | Project for the Establishment of Foundation for the Inland Fish Farming Industry in Myanmar (2014-2018 / USD 4.41m) | 2,362 | 670 | New construction | ◎ |
|  | Project for Rural Community Development in Myanmar (2014-2019 / USD 22m) | 3,870 | 775 | New construction | ◎ |
|  | Project for the Establishment of a Vocational Teacher Training Center in Myanmar (2015-2021 / USD 12.45m) | 6,600 | 800 | New construction | ◎ |
|  | Project for the Establishment of the Myanmar Development Institute (MDI) (2014-2019 / USD 20m) | 6,505 | 1,200 | New construction | ◎ |
|  | Project for the Establishment of an Agricultural Product Distribution Center in Myanmar (2016-2023 / USD 8.37m) | 8,019 | 670 | New construction | △ |
|  | Project for Participatory Rural Development for Underdeveloped Areas using ICT in Myanmar (2020-2025 / USD 20m) | 1700 | 900 | New construction | △ |
|  | Project for the Capacity-Building of Agri-Food Safety and SPS Measures in Myanmar (2021-2026 / USD 12m) | 3500 | 540 | Remodeling | △ |
|  | Project for the Establishment and Capacity-Building of the Korea-Mekong Biodiversity Center (2021-2026 / USD 10m) | 3500 | 1000 | New construction | △ |
| Vietnam | Project for the Capacity-Building of a Judicial Training Center in Vietnam (2013-2016 / USD 9.5m) | 9,626 | 446 | Remodeling + New construction | ◎ |
|  | Project for the Improvement of a Minority Youth Vocational College at Central Highlands in Vietnam (2013-2017 / USD 5m) | 6,294 | 389 | Local construction method | ◎ |
|  | Project for the Establishment of Korea-Vietnam Industrial Technology University in Vietnam (Phase 3) (2013-2017 / USD 6m) | 3,840 | 460 | Local construction method | ◎ |
|  | Project for the Establishment of a General Hospital in Central Region of Vietnam (2006-2012 / USD 35m) | 33,654 | 743 | New construction | ◎ |
|  | Inclusive Rural Development Program in Tuyen Quang Province, Vietnam (2019-2024 / US 18.94m) | - | 600 | Local construction method | ◎ |
|  | Project for Supporting the Establishment of Vietnam-Korea Institute of Science and Technology (V-KIST) in Vietnam (2014-2020 / USD 35m) | 17,000 | 924 | New construction | ◎ |
| Timor-Leste | Project for the Capacity-Building of Tuberculosis Diagnosis and Management in Timor-Leste (2013-2016 / USD 2.1m) | 447 | 2,494 | New construction | ◎ |
|  | Project for Supporting Becora Technical High School in Timor-Leste (2012-2017 / USD 9.04m) | 7,399 | 485 | Remodeling + new construction | ◎ |
|  | Project for Supporting the Establishment of the Fishing Industry Training Center in Timor-Leste (2014-2017 / USD 6m) | 5,318 | 656 | New construction + remodeling | ◎ |
|  | Project for Improving the Maternal Health in Ainaro Region in Partnership with the Timore-Leste Ministry of Health (2015-2020 / USD 4.9m) | 296 | 1,800 | New construction | ◎ |
|  | Project for the Capacity-Building of Sports for Children in Timor-Leste (2020-2024 / USD 7.15m) | 1,436 | 1,000 | New construction | △ |
| Philippines | Project for the Establishment of a Vocational Training Center in Davao City, the Philippines (Phase 2) (2011-2015 / USD 3m) | 1,502 | 866 | Remodeling | ◎ |
|  | Project for the Capacity-Building of Regional Health Care in Iloilo, the Philippines (2013-2016 / USD 7m) | 3,584 | 871 | New construction | ◎ |
|  | Project for the Comprehensive Agricultural Development of New Villages in Quirino, the Philippines (2013-2016 / USD 5m) | 760 | 803 | New construction | ◎ |
|  | Project for the Capacity-Building of Rice Seed Production and Supply in the Philippines (2013-2016 / USD 3.99m) | 1,094 | 1,672 | New construction | ◎ |
|  | Project for the Post-Typhoon Reconstruction of Tolosa Campus of West Visayas State University in the Philippines (2014-2017 / USD 4m) | 4200 | 700 | New construction | ◎ |
|  | Rehabilitation of Felipe Abrigo Memorial Hospital, Referral Hospital of Guiuan Interlocal Health Zone (2015-2022 / USD 5.9m) | 3600 | 806 | New construction | △ |
|  | Project for Sustainable Saemaul Rural Development in Panay Island Upland in the Philippines (2015-2019 / USD 6.5m) | 1365 | 652 | Local construction method | ◎ |
|  | Project for the Establishment of an Advanced Agriculture Research Center at the National University, and Capacity-Building of Higher Education in the Philippines (2021-2026 / USD 14.95m) | 5600 | 1000 | New construction | △ |
|  | Project for Comprehensive Rural Development in Quirino, the Philippines (Phase 2) (2018-2023 / USD 9.5m) | 6615 | 678 | New construction | ◎ |
|  | Project for the Establishment of an Agricultural Industrialization Center and Capacity-Building of Production in Philippines (2020-2023 / USD 6.35m) | 2000 | 450 | New construction | △ |
| Indonesia | Project for the Establishment of Sustainable Total HR Development and Employment Support Platform for the Indonesian Vulnerable Youth (2020-2023 / USD 7.7m) | 3250 | 246 | Extension | △ |
|  | Project for the Establishment of an ICT-based Integrated Knowledge Education Center at the National University in Indonesia (2021-2025 / USD 9.85m) | 6295 | 795 | New construction | △ |
|  | Project for the Capacity-Building of the Indonesian Police Agency's Cyber Crime Investigation (2018-2021 / USD 5.1m) | 1300 | 500 | Remodeling | △ |
| Sri Lanka | Project for the Establishment of an International Conference Center in Hambantota, Sri Lanka (2006-2014 / USD 8.81m) | 8,372 | 848 | New construction | ◎ |
|  | Project for the Nurturing and Retraining of Technical Teachers in Sri Lanka (2015-2025 / USD 17.95m) | 13,000 | 650 | New construction | △ |
| Pakistan | Project for the Establishment of an Agriculture and Stockbreeding Capacity-Building Technology Center at Arid Agriculture University in Pakistan (2012-2016 / USD 3.5m) | 3,300 | 636 | New construction | ◎ |
|  | Project for the Establishment of an ICT Center in Islamabad, Pakistan (2010-2015 / USD 5m) | 3,681 | 723 | New construction | ◎ |
|  | Project for the Establishment of a Water Resources Training Center in Pakistan (2011-2014 / USD 3m) | 2,491 | 590 | New construction | ◎ |
|  | Project for the Establishment of Pak-Korea Testing Laboratory for PV Modules & Allied Equipment (2019-2023 / USD 9.5m) | 2738 | 755 | New construction | △ |
|  | Project for the Establishment of a Nutrition Education Center for Improving Children and Regional Nutrition in Pakistan (2020-2024 / USD 7m) | 3000 | 667 | New construction | △ |
| Nepal | Project for the Establishment of an ICT Center at Tribhuvan University in Nepal (2010-2013 / USD 5m) | 3,126 | 845 | New construction | ◎ |
|  | Ex-post Construction for the Vocational Training Center in Butwal, Nepal (2008-2011 / USD 5.68m) | 5,562 | 593 | New construction | ◎ |
|  | Project for the Establishment of Improved Health and Medicine in the Tikapul region of Nepal (2011-2014 / USD 5.5m) | 4,183 | 514 | New construction | ◎ |
|  | Project for the Establishment of a Technical Training Center at Kathmandu University in Nepal (2011-2014 / USD 3.5m) | 3,056 | 432 | New construction | ◎ |
|  | Project for the Establishment of an Information Disaster Recovery Center (DRC) in Nepal (2013-2020 / USD 5.47m) | 1,000 | 2,000 | New construction | ◎ |
|  | Project for the Establishment of Improved Health and Medicine in the Mugu region of Nepal (2013-2020 / USD 5.4m) | 1,200 | 2,333 | New construction | ◎ |
|  | Project for the Improvement of the Quality of Technical Vocational Education and Training by Capacity-Building of Technical Teachers in Nepal (2015-2022 / USD 5m) | 1,500 | 800 | New construction | ◎ |
|  | Project for Supporting the Reconstruction and Restoration in the Health Sector from Earthquake Damage in Nuwakot District, Nepal (2015-2020 / USD 8.4m) | 3340 | 749 | New construction | ◎ |
|  | Project for the Establishment of a Model Polytechnic to Nurture Construction Technology Personnel in Province No. 2, Nepal (2021-2027 / USD 8.6m) | 3700 | 1005 | New construction | △ |
|  | Project for the Establishment of a Cyber Safety Agency for Capacity-Building of Police in Nepal (2021-2026 / USD 8m) | 2500 | 1000 | New construction | △ |
| Bangladesh | Project for Supporting Middle School IT Training in the Dhaka region of Bangladesh (2012-2014 / USD 3.53m) | 15,098 | 43 | Interior | ◎ |
|  | Project for the Establishment of a Specialized Nursing Graduate School in Bangladesh (2012-2019 / USD 13.75m) | 9,000 | 689 | New construction | ◎ |
|  | Project for the Capacity-Building of Eye Disease Prevention and Treatment in Bangladesh (2014-2023 / USD 8.45m) | 1428 | 1218 | New construction + Remodeling | ◎ |
|  | Project for the Capacity-Building of Technical Training Centers in the Chemical Industry in Bangladesh (2013-2016 / USD 5m) | 2,755 | 581 | New construction | ◎ |
|  | Project for the Capacity-Building of the Vocational Training Center in Rajshahi, Bangladesh (2015-2019 / USD 8.5m) | 6,700 | 522 | New construction | ◎ |
|  | Project for the Capacity-Building of Cyber Crime Investigation in Bangladesh (2012-2015 / USD 3m) | 1,070 | 682 | Remodeling | ◎ |
|  | Project for Supporting the Capacity-Building of College Start-up Training to Promote Youth Start-ups in Bangladesh (2018-2024 / USD 4.3m) | 1248 | 953 | Extension + Remodeling | △ |
| Solomon Islands | Project for the Establishment of a Forest Resource Management Implementation Plan in Solomon Islands (2012-2015 / USD 1.5m) | 100 | 1,700 | New construction | ◎ |
|  | Project for Capacity-Building of Fishery Industry Personnel at the National University in Solomon Islands (2014-2017 / USD 5m) | 1,240 | 1,983 | New construction | ◎ |
| Jordan | Project for the Establishment of Health Centers in 3 regions in Jordan (2014-2018 / USD 5.16m) | 3,594 | 1,085 | New construction + remodeling | ◎ |
|  | Project for the Establishment of a Special School for the Deaf in Jordan (2014-2017 / USD 5.2m) | 3,300 | 970 | New construction | ◎ |
|  | Project for the Capacity-Building of Vocational Training in Jordan (2010-2014 / USD 5m) | 2,200 | 1,073 | New construction | ◎ |
|  | Project for the Establishment of a Technical High School in Zarca, Jordan (2017-2021 / USD 9.88m) | 8768 | 888 | New construction | ◎ |
|  | Project for Building 3 New Schools for KG, Primary, and Secondary Level (JRP. Resilience 3) (2017-2021 / USD 11.1m) | 11543 | 1,040 | New construction | ◎ |
| Palestine | Project for the Establishment of a National Drug Addiction Rehabilitation Center in Palestine (2013-2017 / USD 5m) | 3,800 | 711 | New construction | ◎ |
|  | Project for the Establishment of the Youth Center in Jenin (2013-2018 / USD 3.6m) | 2,440 | 1,107 | New construction | ◎ |
|  | Project for the Establishment of a Bio Research Center in Palestine (2013-2017 / USD 3m) | 2,062 | 970 | New construction | ◎ |
|  | Project for the Establishment of an Institute of Public Administration in Palestine (2014-2018 / USD 7m) | 5,287 | 936 | New construction | ◎ |
|  | Project for the Establishment of a Technical High School in Kupr Nima, Palestine (2010-2014 / USD 3.7m) | 13,597 | 147 | New construction | ◎ |
|  | Project for the Establishment of an ICT Center in Ramallah, Palestine (2011-2014 / USD 3.2m) | 6,360 | 220 | Remodeling | ◎ |
| Iraqi Kurdistan | Project for the Establishment of Modern Basic and Secondary Schools in Sulaymaniyah and Erbil of Kurdistan Region, Iraq (2013-2016 / USD 9.3m) | 9,600 | 913 | New construction | ◎ |
| Uzbekistan | Project for the Capacity-Building of the Technical Training Center in Samarkand, Uzbekistan (2013-2017 / USD 6.4m) | 4,622 | 837 | New construction | ◎ |
|  | Project for the Establishment of a Training Center in Shahrisabz, Uzbekistan and Providing Consultation about Capacity-Building of Vocational Training (2014-2017 / USD 8.5m) | 5,181 | 676 | Remodeling | ◎ |
|  | Project for the Establishment of a Vocation Training Center in Fergana, Uzbekistan (2018-2022 / USD 8.9m) | 5455 | 613 | New construction | ◎ |
|  | Project for the Establishment of a Vocation Training Center in Urgench, Uzbekistan and Supporting the Consolidation of the Vocational Training System Capacity (2020-2024 / USD 14m) | 5320 |  | TBD | △ |
| Turkmenistan | Project for the Establishment of a Vocational Training Center for the Gas Industry in Turkmenistan (2014-2017 / USD 5.9m) | 2,000 | 1,395 | New construction | ◎ |
| Morocco | Project for the Comprehensive Support for Green Technology R&D (2017-2021 / USD 8m) | 1755 | 1,200 | New construction | △ |
| Rwanda | Project for Supporting the Integrated Technical Training Center in Kicukiro, Rwanda (Phase 2) (2013-2016 / USD 5m) | 3,095 | 753 | New construction | ◎ |
|  | Project for the Establishment of an ICT Innovation Center in Rwanda (2013-2015 / USD 5.6m) | 2,542 | 1,393 | New construction | ◎ |
|  | Project for Comprehensive Rural Development in Rwanda (2013-2017 / USD 5m) | 1,698 | 795 | New construction | ◎ |
|  | Project for the Establishment of a Software Specialized High School in Rwanda (2021-2025 / USD 7.1m) | 3239 | 1133 | New construction | △ |
| Mozambique | Project for the Capacity-Building of an Industrial School in Matola, Mozambique (2013-2017 / USD 6.5m) | 15,790 | 205 | Remodeling | ◎ |
| Ethiopia | Project for the Establishment of a Primary School in Akaki, Ethiopia (2010-2015 / USD 2m) | 3,418 | 456 | New construction | ◎ |
|  | Project for the Establishment of a Middle School in Adwa, Ethiopia (2011-2015 / USD 3.7m) | 6,063 | 553 | New construction | ◎ |
|  | Project for the Capacity-Building of Primary Education Through Radio Broadcasting in Oromia Region, Ethiopia (2013-2017 / USD 6.7m) | 1,531 | 758 | New construction | ◎ |
|  | Project for the Establishment of a Vocational Training Center in Tigray Region, Ethiopia (2013-2018 / USD 5.5m) | 5,751 | 484 | New construction | ◎ |
| Uganda | Project for the Establishment of a Fruit Processing Plant in Uganda (2011-2017 / USD 7.4m) | 2,968 | 819 | New construction | ◎ |
|  | Project for the Establishment of a Farming Leader Training Center in Uganda (2011-2015 / USD 3.5m) | 3,332 | 600 | New construction | ◎ |
|  | Project for the Establishment of a Vocational Training Center in Uganda (2011-2017 / USD 4.5m) | 3,788 | 641 | New construction | ◎ |
| Tanzania | Project for the Improvement of Maternity Health Care Services in Chanika, Tanzania (2014-2017 / USD 4m) | 3,378 | 705 | New construction | ◎ |
|  | Project for the Improvement of the PR Center of Serengeti National Park in Tanzania (2015-2017 / USD 1.5m) | 572 | 1,284 | New construction | ◎ |
| Kenya | Project for the Improvement and Capacity-Building of Primary Schools in Kenya (2014-2017 / USD 4m) | 1,768 | 1,386 | New construction | ◎ |
| DR Congo | Project for the Establishment of a National Museum in DR Congo (2011-2019 / USD 20m) | 6,500 | 2,400 | New construction | ◎ |
|  | Project for Comprehensive Rural Development in Kitshini, DR Congo (2013-2017 / USD 3m) | 936 | 460 | New construction | ◎ |
|  | Project for the Capacity-Building of Health Care for Improved Maternity Health in Kwango, DR Congo (2013-2017 / USD 6m) | 3,673 | 395 | New construction + Renovation/Repair | ◎ |
| Angola | Project for the Capacity-Building of Fishery Resources Creation in Angola (2011-2018 / USD 6.45m) | 1,569 | 2,090 | New construction | ◎ |
|  | Project for Teacher's Capacity Building and Community Literacy Development in Angola (Phase 2) (2016-2019 / USD 2.6m) | 1,053 | 1,178 | New construction | ◎ |
| Cote d'Ivoire | Project for the Establishment of the Korea-Cote d'Ivoire Cooperation Center in Cote d'Ivoire (2015-2020 / USD 9.5m) | 4,179 | 2,225 | New construction | ◎ |
| Senegal | Project for the Capacity-Building of Agricultural Technologies in Senegal (2014-2017 / USD 3m) | 2,007 | 650 | New construction + remodeling | ◎ |
|  | Project for the Establishment of an Advanced Technical College (ISEP) in Senegal (2015-2019 / USD 9m) | 6,568 | 750 | New construction | ◎ |
|  | Project for Sustainable, Inclusive Rice Value Chain Development Project in Podor, Senegal (2016-2022 / USD 8.5m) | 492 | 450 | New construction | △ |
|  | Project for the Establishment of a Maternity Health Care System in the Central Region of Senegal (2018-2022 / USD 8m) | 3566 | 614 | New construction | △ |
| Ghana | Project for the Improvement of Maternity Health Care in Volta, Ghana (2013-2017 / USD 6m) | 2,592 | 722 | New construction | ◎ |
|  | Project for the Establishment of the Korea-Ghana Research and ICT Innovation Center at Ghana University in Ghana (2021-2025 / USD 9m) | 3,750 | 926 | New construction | △ |
|  | Project for the Establishment of Ebola Quarantine Centers in Tamale, Ghana (2014-2017 / USD 0.42m) | 777 | 2,450 | New construction | ◎ |
| Nigeria | Project for the Establishment of the Model Schools for Primary and Junior Secondary Education in Nigeria (2013-2018 / USD 15m) | 19,000 | 353 | New construction | ◎ |
|  | Project for the Capacity-Building of E-Government in Nigeria (2013-2019 / USD 8.56m) | 950 | 1758 | New construction | ◎ |
| Cameroon | Project for the Establishment of a National Vocational Training Institute in Cameroon (2013-2017 / USD 6.4m) | 2,686 | 1,118 | New construction | ◎ |
| Guatemala | Project for the Capacity-Building of the Huehuetenango National Hospital on Maternal and Infant Health in Guatemala (2011-2017 / USD 5.1m) | 3,057 | 1,308 | New construction | ◎ |
|  | Project for the Improvement of the Police Education and Training of National Civil Police of Guatemala (2014-2017 / USD 3.8m) | 2,290 | 1,048 | New construction | ◎ |
| Bolivia | Project for the Improvement of the Health and Medical Treatment System and the Capacity-Building of Medical Treatment in Oruro, Bolivia (2010-2018 / USD 12.36m) | 7,058 | 1,281 | New construction | ◎ |
|  | Project for the Assistance of the El Alto Korean Hospital in Bolivia (Phase 3) (2013-2018 / USD 8.4m) | 2,652 | 1,474 | New construction | ◎ |
|  | Project for Agricultural Industrialization and the Capacity-Building of Farmers in the Highlands of Bolivia (2013-2020 / USD 5m) | 2526 | 1,021 | New construction | △ |
| Ecuador | Project for the Establishment of a Healthcare Center in Guayas, Ecuador (2014-2020 / USD 5.82m) | 2,541 | 1,343 | New construction | ◎ |
|  | Project for the Establishment of a Photovoltaic Power Station in Galápagos, Ecuador (2010-2016 / USD 10.1m) | 30,264 | 255 | New construction | ◎ |
|  | Project for the Establishment of an Innovation Center in Yachay Knowledge City, Ecuador (2016-2019 / USD 5m) | 3,000 | 1,000 | New construction | ◎ |
|  | Project for the Establishment of a Start-up Innovation Center in Quito, Ecuador (2020-2026 / USD 9m) | 4,000 | 750 | Remodeling | △ |
| El Salvador | Project for the Establishment of the Korea-El Salvador Medical Center in El Salvador (2013-2017 / USD 3m) | 1,500 | 1,165 | New construction | ◎ |
|  | Project for the Establishment of a National Health Care Education Center and the Capacity-Building of Health Care Education in El Salvador (2019-2022 / USD 6.5m) | 3010 | 1,213 | New construction | △ |
|  | Project for the Capacity-Building of Engineering Training of the ITCA in El Salvador (2021-2025 / USD 5m) | 750 | 1,200 | New construction | △ |
| Colombia | Project for the Establishment of the Korea-Colombia Friendship Integral Rehabilitation Center in Colombia (2007-2016 / USD 11.5m) | 12,487 | 877 | New construction | ◎ |
| Paraguay | Project for the Establishment of an Advanced Vocational Training Institute in Paraguay (2010-2015 / USD 5.38m) | 3,889 | 843 | New construction | ◎ |
|  | Project for the Establishment of a General Hospital in San Pedro, Paraguay (2019-2012 / USD 5.45m) | 6170 | 534 | New construction | ◎ |
|  | Project for the Capacity-Building of Maternal-Infant Health Care of San Pablo Hospital in Paraguay (2013-2018 / USD 6.88m) | 4,855 | 1,149 | New construction | ◎ |
|  | Project for the Establishment of a Health and Medical Treatment System and the Capacity-Building of Primary Health Care in Limpio City, Central Province, Paraguay (Phase 3) (2016-2022 / USD 13.9m) | 1,400 | 1,000 | New construction + Extension | ◎ |
|  | Project for the Establishment of a Long-term Health and Social Care Facility for the Elderly in Paraguay (2016-2021 / USD 10m) | 5907 | 898 | New construction | ◎ |
|  | Project for the Capacity-Building of Aviation Experts in Paraguay (2019-2022 / USD 11m) | 3570 | 1000 | New construction | △ |
| Peru | Programs for Health Promotion in Lima and Callao, Peru (2013-2017 / USD 7.85m) | 2,399 | 1,292 | New construction | ◎ |
|  | Project for the Capacity-Building of Health and Medical Treatment in Chanchamayo, Peru (2013-2017 / USD 2.5m) | 1,397 | 1,274 | New construction | ◎ |
|  | Project for the Capacity-Building of Health and Medical Treatment in Pachacuteq, Peru (2013-2017 / USD 3.37m) | 2,281 | 1,130 | New construction | ◎ |
|  | Project for Rural Development in Ccorao, Cusco, Peru (2010-2012 / USD 1.276m) | 1,342 | 627 | New construction | ◎ |
| Haiti | Project for the Establishment of an Apparel Training Center in Caracol, Haiti (2013-2016 / USD 3.5m) | 1,300 | 702 | New construction | ◎ |
| Dominican Republic | Project for the Prevention of Teen Pregnancy and Strengthening the Comprehensive Health of Adolescents in the Dominican Republic (Phase 3) (2018-2023 / USD 4m) | 866 | 1040 | New construction | △ |
|  | Project for the Socio-Economic Capacity-Building of Women in 6 Eastern Provinces of the Dominican Republic (2020-2024 / USD 5.5m) | 500 | 950 | New construction | △ |
| Honduras | Project for the Capacity-Building of Teachers' ICT Utilization in Honduras (2018-2021 / USD 1.8m) | 535 | 450 | Remodeling | △ |